## Tabelle1
Item Type | Sprint Number | Task Name | Time [h]
Sprint | 1 | Design Main User Interface | 3
Sprint | 1 | Create a class that will handle all Database related actions. | 3
Sprint | 2 | Bind the references needed for the Excel database driver | 2.5
Sprint | 2 | Implement a DataGridView for Displaying the Data pulled from the DB | 3.5
Sprint | 2 | Build a file choosing option for selecting the wanted Excel sheet, with limiting extension (.xls, xlsx) | 1.5
Sprint | 3 | Implement a permanent saving of the DB path so that there is no need of setting it every time the program opens. (Preference Saving) | 2.5
Sprint | 3 | Build a Help section for additional information on how the Excel sheet needs to be organized (Columns) | 2.5
Sprint | 3 | Create a new member user interface | 2.5
Sprint | 4 | Handle all necessary CRUD operations with the DB, display results in a table. | 9
Sprint | 4 | Implement onClick generation of a new Window with the detailed info of the clicked member in the table. | 3
Sprint | 4 | Build a member info (new payment) update section in the detailed information Window | 2.5
Sprint | 5 | Implement the addition of a new Member in the Database via the New Member Window | 3.5
Sprint | 5 | Implement the BackupManager, making a Backup before each change in the DB. | 4
Sprint | 5 | Implement removal of members form the DB | 4.5
|  | Software development total time | 47.5